## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
The project is going well. I had to wait to do the admin pages until I get the user pages fully functional to understand exactly what admin users need to be able to handle. I’m ahead in terms of backend with a functional log in system. Some Minor design changes. | 
Status as of | 03/27/2019
Business Lead | Jim Worth
Project Manager | Jonathan T. Risoldi
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/21 | 
Design |  | 90% | 2/27 | 
Coding |  | 50% | 4/14 | 
SIT - System Test |  | 0% | 4/21 | 
UAT User Acceptance Test |  | 0% | 4/29 | 
Training and Doc |  | 0% | 5/1 | 
Deployment |  | 0% | 5/1 | 
Go Live |  | 0% | 5/1 | 
Hyper Care |  | 0% | 5/7 | 
# | Key Accomplishments (Current Period)
1 | Completed Login System
2 | Worked on Registration System. In progress.
3 | Learning Backend information
# | Upcoming Activities (Next Period through (04/03/2019)
1 | Finish registration system.
2 | Start working with sessions for individual user profiles.
3 | Populate website via database.
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Search functionality may be harder than expected and may be delayed or offer less functionality. | Med | Med | I’m looking into options to fix this issue but it is not a high priority yet. | Jonathan | med | 04/14
2 |  |  |  |  |  |  | 
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 |  |  |  |  |  |  | 
Cairn Unify