## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
Due to unforeseen circumstances not Related to the project, the project is running behind schedule. Coding and SIT pushed back till 4/24 | 
Status as of | 04-17-2019
Business Lead | Jim Worth
Project Manager | Jonathan Risoldi
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/21 | 
Design |  | 100% | 2/27 | 
Coding |  | 77% | 4/14 | 4/24
SIT - System Test |  | 50% | 4/21 | 4/24
UAT User Acceptance Test |  | 0% | 4/29 | 5/1
Training and Doc |  | 0% | 5/1 | 
Deployment |  | 0% | 5/1 | 
Go Live |  | 0% | 5/1 | 
Hyper Care |  | 0% | 5/7 | 
# | Key Accomplishments (Current Period)
1 | Fixed registration errors that caused registration to fail.
2 | Profiles are now functional.
3 | Started work on images and user profile edits.
# | Upcoming Activities (Next Period through (04/24/2019)
1 | Enable users to edit their profiles
2 | Basic search functionality
3 | Employee system
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Current ability to implement images for user profiles is limited. May not be ready for initial launch. | Med | Med | Working to mitigate the problem by further testing and education. | Jonathan | Med | 04/25?
2 | Search functionality will be limited for initial launch. | Med | Med | Working on ways to implement search. | Jonathan | Hi | 04/25
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Project is pushed back due to several different circumstances. |  |  | Coding and testing are extended. | Jonathan |  | 04/25
Cairn Unify