## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
Coding and SIT and are complete. Due to deadlines some functionality is excluded or limited from Cairn Unify, but can be done through PHPMyAdmin. | 
Status as of | 05-01-2019
Business Lead | Jim Worth
Project Manager | Jonathan Risoldi
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/21 | 
Design |  | 100% | 2/27 | 
Coding |  | 100% | 4/14 | 4/24
SIT - System Test |  | 100% | 4/21 | 4/24
UAT User Acceptance Test |  | 100% | 4/29 | 5/1
Training and Doc |  | 95% | 5/1 | 5/7
Deployment |  | 100% | 5/1 | 
Go Live |  | 100% | 5/1 | 
Hyper Care |  | 0% | 5/7 | 
# | Key Accomplishments (Current Period)
1 | Enabled users to Edit profiles.
2 | Search functionality is complete.
4 | Did some documenting
# | Upcoming Activities (Next Period through (05/07/2019)
1 | Hypercare
2 | More Documentation.
3 | 
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 |  |  |  |  |  |  | 
2 |  |  |  |  |  |  | 
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Some functionality was not able to be put into Unify due to deadlines. | High | Low | Features can be implemented in future versions of Cairn Unify | Jonathan |  | Next Version
Cairn Unify
# | Key Accomplishments (Current Period)
1 | UAT finished
2 | Fixed some bugs from SIT and UAT
3 | Added features per request.