## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
Project starting to run into unforeseen issues, slowing down progress. Issues are being worked on to be resolved. Working with others to figure out best path. | 
Status as of | 27-Feb-19
Business Lead | Jim Worth
Project Manager | Jonathan T. Risoldi
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/21 | 02/27
Design |  | 95% | 2/27 | 02/27
Coding |  | 70% | 4/14 | 02/27
SIT - System Test |  | 0% | 4/21 | 02/27
UAT User Acceptance Test |  | 0% | 4/29 | 02/27
Training and Doc |  | 0% | 5/1 | 02/27
Deployment |  | 0% | 5/1 | 02/27
Go Live |  | 0% | 5/1 | 02/27
Hyper Care |  | 0% | 5/7 | 02/27
# | Key Accomplishments (Current Period)
1 | Populated the News Section via the Database
2 | Made progress on creating profiles. Still on progress.
3 | 
# | Upcoming Activities (Next Period through (04/10/2019)
1 | Finish Profile work.
2 | Finish registration functionality.
3 | Start search functionality.
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Backend Functionality could be a potential threat to the project. | High | Med | Working on ways to mitigate the problem including extra training. | Jonathan | Hi | 04/14
2 | Mobile Friendly Issues | Low | Med | Working on mobile first development | Jonathan | Med | Closed
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | There are some mobile friendly issues that need to be resolved | Low | Med | Working on mobile first development | Jonathan | Hi | Closed
Cairn Unify
1 | Working on profiles created an unforeseen problem with completing the registration functionality. | Low | Med | May have to push back time line. Working on finishing profiles to finish registration. | Jonathan | Hi | 04/14