## Slide 1
SUMMARY ASSESSMENT | 
Risk Level | 
Main Reasons for Assessment of Current Risk Level | 
The project is going well so far. Front end development is mostly finished. I am a little bit behind on the front end development but the work should not take too long to catch back up. May add some minor tweaks to the front end. Starting to work on backend things. | 
Status as of | 03/20/2019
Business Lead | Jim Worth
Project Manager | Jonathan T. Risoldi
Key Workstream Milestones |  |  |  | 
Milestone | Risk Level L  H | %-Done | Orig Due Dt | Current Due
Planning |  | 100% | 2/21 | 
Design |  | 90% | 2/27 | 
Coding |  | 40% | 4/14 | 
SIT - System Test |  | 0% | 4/21 | 
UAT User Acceptance Test |  | 0% | 4/29 | 
Training and Doc |  | 0% | 5/1 | 
Deployment |  | 0% | 5/1 | 
Go Live |  | 0% | 5/1 | 
Hyper Care |  | 0% | 5/7 | 
# | Key Accomplishments (Current Period)
1 | Completed front end coding on the connect page.
2 | Started front end work on the admin pages.
3 | 
# | Upcoming Activities (Next Period through (03/06/2019)
1 | Finish front end development on admin pages.
2 | Start building backend.
3 | 
Key Risks (to be reported to Stakeholders) |  |  |  |  |  |  | 
RAID# | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 | Backend Functionality could be a potential threat to the project. | med | High | I’m trying to learn backend stuff | Jonathan | Hi | 04/14
2 |  |  |  |  |  |  | 
Key Issues (to be reported to Stakeholders) |  |  |  |  |  |  | 
Issue | Risk Short Title | Prob | Impact | Mitigation | Owner (s) | Priority | Due Date
1 |  |  |  |  |  |  | 
Cairn Unify