## Timesheet
Student Name: | Jonathan T. Risoldi
Date | 2019-05-08 |  | Plan vs. Actual Analysis
Project Name | Cairn Unify
| Project Phase | Plan | Actual | Difference
| Planning | 6 | 5 | 1
| Design | 6 | 4 | 2
| Coding | 80 | 99.5 | -19.5
| SIT | 8 | 8 | 0
| UAT | 8 | 4 | 4
| Training / Documentation | 2 | 8 | -6
| Deployment | 8 | 8 | 0
| Hypercare | 15 | 15 | 0
|  | 133 | 151.5 | -18.5
Period 1 - 1st through 15th
Period 2 - 16th through month-end